TradePe / ScreenDesk Channel Plan & Launch Plan Go-to-Market Strategy — Section 4 IIM Calcutta · Group 2 Capstone · July 2026

| CHANNEL PLAN How we reach, engage, and convert the right customers — through direct sales, referral partners, and content. | LAUNCH PLAN The week-by-week roadmap from prototype to first paying customer, across three phases. | THE GOAL Three paying customers, ₹15–20L ARR, and two referenceable case studies within 9 months of launch. |
| --- | --- | --- |

This document covers two things: (1) the Channel Plan — which paths we use to find and win customers, and (2) the Launch Plan — the step-by-step timeline from today to first commercial revenue. Together they answer: "How exactly do we get from a working prototype to a paying customer base?"

Section 1 Channel Plan How we reach and convert customers — the routes to market.

Why Channel Strategy Matters for ScreenDesk

Compliance tools are not bought the way consumer apps are. A compliance officer does not search Google for "best sanctions screening software" and sign up with a credit card. They buy from vendors they trust — or that someone they trust has recommended. That is why channel strategy for ScreenDesk is primarily about trust, not advertising.

The #1 buying signal in B2B compliance software: "A peer at another fintech told me they use it and it works." Everything in our channel plan is designed to generate that conversation.

Our Three Channels — In Priority Order

We will use three channels. In Year 1, Channel 1 is everything. Channels 2 and 3 build in parallel and take over progressively in Years 2 and 3.

| Channel | What It Is | Year 1 Mix | Year 2 Mix | Year 3 Mix |
| --- | --- | --- | --- | --- |
| 1. Direct Sales | Founder-led outreach and demos, converting pilots to paid accounts | 90% | 60% | 40% |
| 2. Partner Referral | Compliance consultants and fintech associations recommending ScreenDesk | 10% | 30% | 35% |
| 3. Inbound / Content | Thought leadership and community presence generating warm leads | < 5% | 10% | 25% |

Section 1A Channel 1 — Direct Sales The primary route to market in Year 1.

Who Sells and How

In Year 1, the founders sell. This is deliberate — not a temporary workaround. The first 10 customers need someone who can answer hard questions about the product architecture, regulatory positioning, and how the AI works. Only the founding team can do that credibly right now. A hired sales rep comes after the playbook is proven.

| Stage | What Happens | Who Owns It | Typical Duration |
| --- | --- | --- | --- |
| 1. Identify | Find a fintech with the right profile: RBI-licensed, cross-border payments, 1–5 analysts, no dedicated screening tool | Founder | 1–2 weeks of research |
| 2. Warm Intro | Get introduced through IIM Calcutta alumni network, a mutual contact, or a fintech association event — cold outreach is a last resort | Founder + alumni network | Ongoing; target 5 intros per month |
| 3. Discovery Call | A 30-minute call to understand their current screening process, volume, and biggest pain point. We listen first, pitch second. | Founder | 30 minutes |
| 4. Demo | A live 45-minute demo using their industry's typical alert profile (UAE corridor, trade finance names). We show the evidence card, the audit trail, and the AI rationale — not the settings page. | Founder | 45 minutes + 15 min Q&A |
| 5. Pilot Offer | Offer a free 60–90 day pilot with a defined success metric agreed upfront. Both sides sign a simple one-page pilot agreement. | Founder | Same week as demo |
| 6. Pilot-to-Paid | At week 4 and week 8, review the metrics together. If the numbers are good, propose the paid contract. | Founder + CSM | Week 4 and Week 8 of pilot |

Our Warm Introduction Network — Year 1 Priority

Cold outreach conversion rates in B2B compliance are very low (< 2%). We focus almost entirely on warm introductions through three networks:

| 1 | IIM Calcutta Alumni Network IIM Cal alumni are spread across Indian fintech, banking, and consulting. Many sit on compliance committees or know the MLRO at a target company. A single credible introduction from a shared alumnus converts 5–8x better than a cold email. We map the alumni network to target companies before any outreach begins. |
| --- | --- |

| 2 | Fintech Accelerator and Investor Networks Y Combinator India, Antler, Sequoia Surge, and BharatPe-era founders are all connected to compliance-heavy fintechs. A warm intro from a shared investor or accelerator peer carries near-founder-level credibility. We maintain a list of shared investors and ask for introductions to portfolio companies in our ICP. |
| --- | --- |

| 3 | The Compliance Community Itself ACAMS India chapter events, IBA compliance working groups, and FIU-IND outreach programmes bring compliance officers together. Being present — as a speaker, panelist, or working group member — means we meet our buyers where they already gather. One event introduction is worth 50 cold emails. |
| --- | --- |

Direct Sales Targets — Year 1

| Month | Activity Target | Pipeline Target | Revenue Target |
| --- | --- | --- | --- |
| Months 1–2 | 10 discovery calls completed | 3 pilots agreed and started | ₹0 (free pilot phase) |
| Month 3 | Week 4 pilot check-ins done | 1st conversion conversation begun | ₹0 (still in pilot) |
| Month 4–5 | 2 pilots converted to paid | 3 new pilots in pipeline | ₹2.4L–₹4.8L MRR from first customers |
| Month 6–7 | 1 more pilot converted | 5 new discovery calls per month | ₹5–8L MRR |
| Month 8–9 | Second cohort of 3 pilots started | 2 more conversions expected | ₹15–20L ARR run rate |

Section 1B Channel 2 — Partner Referral Trusted third parties who recommend ScreenDesk to their clients.

Why Partners Matter

A compliance consulting firm tells a fintech: "Use ScreenDesk — we've seen it work." That recommendation is worth six months of relationship building. Partners who already have trust relationships with our target customers can open doors we cannot open ourselves.

Partner Type 1 — Compliance Consulting Firms

Big-4 and mid-tier consulting firms (Deloitte Risk, EY Forensics & Integrity, PwC Financial Crime, KPMG Regulatory) advise Indian fintechs on their compliance programmes. They are not competitors — they design the compliance framework; ScreenDesk runs it.

| What We Offer Partners | What Partners Give Us | Economics |
| --- | --- | --- |
| A tool they can recommend to fintech clients as "the workflow layer" on top of the compliance programme they designed | Referrals to qualified MLROs and compliance heads who already have a consulting relationship and a budget | 15% referral commission on Year 1 revenue from referred customers |
| Co-branded methodology materials: "ScreenDesk powers the sanctions screening workflow in our compliance programme" | Credibility in sales conversations — a Big-4 recommendation removes the "are you trustworthy?" question | Partner portal access + quarterly partner briefing on product roadmap |
| Training for their analysts on how to use ScreenDesk during client engagements | A reason to bring ScreenDesk into any new fintech compliance engagement they win | Named "implementation partner" status on our website after first 2 joint customers |

Partner Type 2 — Fintech Associations and Industry Bodies

The India Fintech Forum (IFF), Fintech Association for Consumer Empowerment (FACE), and NASSCOM Fintech are trusted voices in the Indian fintech ecosystem. A recommendation or "associate member" status from these bodies gives ScreenDesk legitimacy with companies we have not yet directly reached.

ACAMS India Chapter: Professional body for anti-money laundering compliance officers. Being a chapter sponsor or speaker puts ScreenDesk in front of 500+ Indian AML professionals.

India Fintech Forum (IFF): Membership gives access to a directory of 200+ Indian fintechs, most of whom face exactly the compliance challenges ScreenDesk solves.

IBA (Indian Banks' Association): Working group membership gives credibility with the banking segment we want to enter in Phase 3.

Partner Type 3 — AD Category-I Banks (Correspondent Banking)

Many of our target fintechs (PA/AD Category-II licence holders) rely on an AD Category-I bank as their correspondent bank for cross-border settlements. If an AD bank recommends ScreenDesk to their fintech clients, it is essentially a regulatory endorsement — the most powerful possible referral in this market.

Target: Identify 1–2 progressive compliance heads at mid-tier AD banks (IDFC First, RBL, IndusInd) who are willing to recommend ScreenDesk to their fintech clients as a "good practice" tool. This is a 12–18 month relationship investment, not a quick win — but the payoff is enormous.

| Partner Activation Timeline | What We Do | Expected Outcome |
| --- | --- | --- |
| Month 1–2 | Identify 5 target consulting firms; get intro calls with their financial crime practice leads | 2–3 firms agree to explore a referral relationship |
| Month 2–4 | Joint pilot: invite one consulting firm to co-present ScreenDesk to a shared client as part of a compliance programme design engagement | 1 joint customer acquired through consulting partner |
| Month 3–6 | ACAMS India Chapter sponsorship; attend 2–3 fintech association events as a speaker or exhibitor | 5–10 warm leads from community presence |
| Month 6–12 | Formalise partner programme: signed referral agreements, partner portal, co-marketing materials | Partner channel generating 15–20% of new leads |

Section 1C Channel 3 — Inbound & Content Building the long-term pipeline through thought leadership and community.

What Inbound Means for a Compliance Tool

Compliance officers read. They are professional, detail-oriented, and they trust written expertise over sales pitches. A well-written article on "How to handle OFAC name-matching challenges in cross-border payments" will be read, shared, and remembered by exactly the people we want to sell to. Inbound is slow to start but compounds over time — every piece of content is a permanent asset.

Content Themes — What We Write About

| Topic Area | Example Titles | Why It Works |
| --- | --- | --- |
| False positive reduction | "5 reasons your OFAC screening is generating too many false alarms" "How name transliteration causes 40% of false positives in UAE corridor payments" | The #1 daily pain for analysts — anyone facing this will find and read it |
| FIU-IND / RBI compliance | "What FIU-IND actually looks for in a sanctions screening audit" "RBI AD Category-II licence: what your compliance programme needs to include" | Specific regulatory context that generalist vendors do not cover — our India-native advantage |
| AI in compliance | "Why AI should never make a compliance decision — and what it should do instead" "The difference between an AI screening tool and an AI compliance copilot" | We can own the "responsible AI in compliance" conversation in India before anyone else does |
| Benchmarking | "India Cross-Border Compliance Benchmarking Report — 2026" "How long does a sanctions screening alert actually take to disposition? India data." | Original data from our customer base — impossible to replicate; becomes a must-read for compliance teams |

Where We Publish

LinkedIn: Primary platform. Compliance officers are active on LinkedIn; they share articles, comment on regulation news, and follow industry voices. We post 3–4 times per week — short insights, not long essays.

ACAMS India Newsletter: Contribute one article per quarter. Reaches 500+ credentialed AML professionals directly in their inbox.

Company blog (tradepe.in/blog): Home for longer pieces — 1,000–1,500 word deep dives that rank on Google and can be shared with prospects during sales conversations.

Annual Benchmarking Report: Published free, promoted through ACAMS and IFF. This one asset does more for brand credibility than 12 months of ads.

Inbound Targets

| Metric | Month 3 Target | Month 6 Target | Month 12 Target |
| --- | --- | --- | --- |
| LinkedIn followers (company page) | 200 | 500 | 1,500 |
| Blog visitors per month | 100 | 500 | 2,000 |
| Inbound leads per month | 0–1 | 2–3 | 5–8 |
| Inbound-sourced customers | 0 | 0–1 | 2–3 |
| Benchmarking report downloads | N/A | 100+ | 500+ |

Note: Inbound is a Year 2+ revenue driver. In Year 1 it is a brand-building and credibility investment. We track it, but we do not depend on it for the first 9 months of revenue.

Section 2 Launch Plan The step-by-step timeline from prototype to first commercial revenue.

The Launch in Three Phases

We do not launch with a press release and a pricing page. We launch by signing three design-partner pilots, delivering measurable value, and converting them to paid customers. Only after that do we make any public market announcement.

| Phase | Name | Duration | Goal | Revenue |
| --- | --- | --- | --- | --- |
| Phase 0 | Pre-Launch — Fix the Blockers | Now → Launch Day (4–6 weeks) | Resolve all three technical launch blockers | ₹0 — no customers yet |
| Phase 1 | Design Partner Pilots | Months 1–3 | Run 3 pilots; prove the product delivers value | ₹0 — pilots are free |
| Phase 2 | Paid Conversion & Market Entry | Months 3–6 | Convert 2 of 3 pilots; publish first case study | ₹5–10L MRR |
| Phase 3 | Scale | Months 6–12 | 8–12 paying customers; activate partner channel | ₹15–20L ARR run rate |

PHASE 0 Pre-Launch — Fix the Blockers Now → Launch Day (estimated 4–6 weeks)

▶ Fix Blocker 1: Connect live watchlist feeds (OFAC, UN, EU, PEP) with daily refresh ▶ Fix Blocker 2: Build login system with 3 roles (Analyst, Compliance Officer, MLRO) ▶ Fix Blocker 3: Switch to production web server (Gunicorn + Nginx + HTTPS) ▶ Prepare a one-page pilot agreement template (legal review required) ▶ Build the baseline measurement template: current MTD, alert volume, rationale coverage ▶ Identify and shortlist 10 design-partner candidates from the warm intro network ▶ Prepare the demo environment: 3 realistic scenarios for UAE corridor, trade finance, PEP screening ▶ Set up the customer success workflow: onboarding checklist, week 4 check-in template, week 8 review template

Pre-Launch Checklist — Nothing Ships Without These

| Technical Readiness |  |
| --- | --- |
| Live OFAC SDN watchlist connected and refreshing daily | BLOCKER — must complete |
| Live UN Consolidated Sanctions List connected | BLOCKER — must complete |
| Live EU Financial Sanctions Files connected | BLOCKER — must complete |
| Commercial PEP database integrated (Dow Jones / LexisNexis) | BLOCKER — must complete |
| Watchlist freshness monitor active (MLRO alert if list > 24h stale) | BLOCKER — must complete |
| Login system live: Analyst / Officer / MLRO roles | BLOCKER — must complete |
| Production web server (Gunicorn + Nginx, HTTPS, debug=False) | BLOCKER — must complete |
| IP allowlist configured for each customer environment | Pre-launch required |
| Environment-managed secrets (no API keys in source code) | Pre-launch required |
| All 155 automated tests passing on production build | Pre-launch required |

| Sales & Legal Readiness |  |
| --- | --- |
| Pilot agreement template reviewed by a lawyer | Pre-launch required |
| Master Services Agreement (MSA) template with liability clause ready | Pre-launch required |
| Data processing agreement (for any customer personal data) | Pre-launch required |
| Demo environment with 3 realistic scenarios prepared | Pre-launch required |
| Onboarding checklist and user guide written (Analyst + MLRO versions) | Pre-launch required |
| Baseline measurement template prepared for each pilot customer | Pre-launch required |
| 3 design-partner candidates identified and intro calls booked | Pre-launch required |

PHASE 1 Design Partner Pilots Months 1–3 ¦ Goal: 3 pilots running, producing real data

▶ Launch 3 pilots simultaneously — not sequentially (parallel pilots reduce concentration risk) ▶ Agree on success metrics with each pilot customer before go-live (baseline MTD and rationale coverage) ▶ Conduct mandatory Week 1 onboarding session: analyst training + MLRO briefing on recommendation-vs-decision distinction ▶ Track daily: alerts screened, mean time-to-disposition, AI rationale acceptance rate ▶ Week 4 check-in with each customer: share metrics vs. baseline; diagnose any friction; fix immediately ▶ Week 6: identify which pilots are tracking well for conversion; begin conversion conversation with MLRO ▶ Week 8: formal review meeting with MLRO + Head of Compliance; present 8-week metrics summary ▶ Begin second cohort outreach in Month 2 — do not wait for Phase 1 to close before building next pipeline

Design Partner Selection Criteria

Not every fintech is a good design partner. We select carefully — a bad pilot wastes 90 days and produces no referenceable case study. We look for:

| Criterion | Why It Matters |
| --- | --- |
| Processes 40+ cross-border screening alerts per day | Below this volume, the time savings are hard to measure convincingly |
| Has a named MLRO or Head of Compliance who will sponsor the pilot | Without a buyer sponsor, pilots stall at the analyst level and do not convert |
| Currently using a manual or spreadsheet-based process | Customers already using a (bad) tool need to uninstall it — more friction than starting fresh |
| UAE, Singapore, or US corridor — not exclusively domestic payments | Cross-border payments face the most complex sanctions screening requirements; this is where our value is highest |
| Willing to share anonymised metrics for a case study after the pilot | We need referenceable data to win the next customer |
| RBI-licensed: PA (Payment Aggregator) or AD Category-II | These are the regulated entities with a legal obligation to screen — the pain is regulatory, not optional |

Week-by-Week Pilot Timeline

| Timeframe | Focus | Key Milestone / Deliverable |
| --- | --- | --- |
| Week 1 | Onboarding | All analysts trained; baseline MTD and rationale coverage recorded; go-live on live production build |
| Week 2 | Early data collection | First 5 days of screening data in system; any UI or workflow friction flagged and fixed |
| Week 3 | Stabilisation | False positive rate trending; analyst habits forming; MLRO reviews first dashboard summary |
| Week 4 | Mid-pilot check-in (critical) | Metrics review with MLRO and analyst lead; decision: continue, adjust thresholds, or escalate issues |
| Week 5–6 | Deepening usage | Analyst begins using AI-drafted rationales regularly; second screening scenario type introduced if ready |
| Week 7 | Conversion conversation begins | Informal conversation with MLRO: "What would it take to make this permanent?" |
| Week 8 | Formal 8-week review | Full metrics presentation: MTD improvement, false positive rate, rationale coverage, override rate vs. baseline |
| Week 9–12 | Decision and conversion | MLRO presents to Head of Compliance or CFO; contract negotiated; pilot either converts or extends |

PHASE 2 Paid Conversion & Market Entry Months 3–6 ¦ Goal: First paid revenue; first public case study; market presence established

▶ Convert 2 of 3 Phase 1 pilots to paid contracts (target: Starter or Professional tier) ▶ Start second cohort of 3 pilots in Month 4 (using lessons learned from Phase 1) ▶ Publish first anonymised case study: MTD improvement % and rationale coverage improvement from Pilot 1 ▶ Attend ACAMS India chapter event as speaker or exhibitor; distribute benchmarking survey ▶ Activate first consulting firm referral partnership (target: 1 joint pilot by Month 6) ▶ Fintech association membership activated: IFF, NASSCOM Fintech (or equivalent) ▶ Begin building the MLRO benchmarking dataset for the Year 1 annual report ▶ Hire first Customer Success Manager (CSM) if MRR exceeds ₹5L — the founding team cannot run pilots and sales simultaneously at this scale

Pricing Conversation — How We Convert a Pilot to Paid

The conversion conversation is always anchored to metrics, not features. We never say "here is what the product does." We say "here is what the last 8 weeks showed."

| 1 | Lead with the number that matters most to the MLRO Rationale coverage rate. Before ScreenDesk: ~40% of decisions had a documented reason. After 8 weeks: 100%. That is the audit readiness improvement in one number. No MLRO who has been through an FIU-IND inspection will argue with that. |
| --- | --- |

| 2 | Add the analyst productivity number Mean time-to-disposition: from X minutes per alert to Y minutes. Multiply by daily alert volume and you get "hours per week saved." That is an easy cost-justification calculation for the Head of Compliance. |
| --- | --- |

| 3 | Make the pricing feel small next to the alternative ₹12,000–14,000 per analyst per month is less than two days of a junior compliance hire's fully-loaded cost. Frame it that way: "You're getting a tool that makes your existing team twice as productive, for less than the cost of adding a part-time resource." |
| --- | --- |

| 4 | Offer continuity, not a switch The pilot data, the audit trail, and the case history all live in ScreenDesk. Walking away means losing 8 weeks of documented compliance history. That is a switching cost the MLRO will feel — use it gently but honestly. |
| --- | --- |

PHASE 3 Scale Months 6–12 ¦ Goal: 8–12 paying customers, partner channel active, Phase 2 segment entered

▶ Launch Phase 2 segment outreach: trade-finance NBFCs and commodity exporters (larger deal size, longer cycle) ▶ Formalise the partner programme: signed referral agreements with 2–3 consulting firms ▶ Begin the RBI Regulatory Sandbox application process ▶ Publish the first India Cross-Border Compliance Benchmarking Report (anonymised from customer data) ▶ Hire dedicated sales head (if MRR > ₹10L) — founder transitions from selling to supporting sales ▶ First "bank-adjacent" pilot: AD Category-I bank remittance division or large NBFC with 10+ analysts ▶ Product expansion: FEMA outward remittance workflow, IEC verification, GST-PAN cross-referencing ▶ Evaluate Series A fundraise timing based on NRR and pipeline velocity

Phase 3 — What Good Looks Like at Month 12

| Metric | Month 12 Target | What It Signals |
| --- | --- | --- |
| Paying customers | 8–12 | Enough for statistical NRR measurement and genuine word-of-mouth |
| ARR run rate | ₹15–20L | Viable commercial business; Series A fundraise timing window opens |
| Net Revenue Retention | > 110% | Customers are expanding seats and upgrading plans — the product has real stickiness |
| Partner-sourced revenue | 15–20% of new ARR | Partner channel is working; direct sales is not the only growth engine |
| Referenceable customers | 3+ | Can give investor or prospect references on request |
| Case studies published | 2 (anonymised) | Sales tool that converts cold interest into pilot requests |
| Inbound leads per month | 3–5 | Content is starting to generate its own pipeline |

Channel & Launch — Five Things to Remember

| 1 | In Year 1, the founders sell. That is the plan — not a gap in the plan. The first 10 customers need someone who can answer hard technical and regulatory questions. A sales hire comes after the first 5 customers prove the value proposition in the market. Hiring sales too early wastes money and produces weak results. |
| --- | --- |

| 2 | Warm introductions are the channel. Cold outreach is the fallback. Every sales conversation should start from a mutual introduction — IIM alumni network, shared investor, fintech association contact. We track our warm intro pipeline before we build anything else. |
| --- | --- |

| 3 | Run three pilots simultaneously, not one at a time. Sequential pilots mean 9 months to get 3 data points. Simultaneous pilots mean 3 months. We can absorb the operational load — three free pilots at 1–5 analysts each is manageable. And if one does not convert, we have two others moving forward. |
| --- | --- |

| 4 | The Week 4 check-in is the most important meeting in the pilot. If a pilot is going wrong, Week 4 is when we can still fix it. Week 8 is too late to change habits. The MLRO must be in the Week 4 meeting — not just the analyst. |
| --- | --- |

| 5 | Nothing goes to market before the three technical blockers are resolved. No live watchlist feeds, no production login system, no secure web server — these are not "nice to haves before launch." They are conditions without which ScreenDesk is a demo, not a product. The launch date is determined by when these three things are done, not by a calendar. |
| --- | --- |

TradePe / ScreenDesk — Channel Plan & Launch Plan. Part of the Go-to-Market Strategy document set. All data is synthetic; no real individuals, entities, or financial transactions are represented. IIM Calcutta Group 2 Capstone, July 2026.